## 2017
2017 Action Items for WTFUSA
Number | Item | Discription | Date in | Assign to | Discussion | Chair Position | Final Wording | COMMENTS/STATUS | Agreed -or Not | Close Date
1 | Name | With us representing all Disabilities should we change our Name? | 2016-07-25 | Phil | I make a motion to rename to Adaptive Track & Field USA. ATFUSA.org | Yes | Rename DBA Name to Adaptive Sports USA | We need to Vote Prior to Meeting so we can publish Site | Voted - Yes | 2016-11-01
2 | WEBSITE | It is Randy, Pam and my opinion that we must have or own Website. | 2016-07-25 | Phil | (PG, RC) With the mess ASUSA is in with respect to the Website I think we need a consistant place for our information that APUSA can Hyperlink to. At my expense I will pt up the site and if we vote yes reimburse the cost later. We can then use the site to also raise funds specific to Athetics. Cost will be about 130 per year. | Yes | Put up a ATFUSA Web site | In progress. Most of the pages are written. Jesie has proofed most. I have purchased the WEB site at Go Daddy. Will publish for us to view this weekend. | Voted - Yes | By 12/31/2016
3 | Sales | Continue to sell implements frm Randy for funding. | 2016-07-25 | Randy | We are making money and proviing a value we should continue and possibly add items. Javs for 2017. | Yes | Continue to market Shots, and possibly Add Jav's | Randy please prepare and share a 2016 (to date)Sales report | Voted - Yes
4 | B standard rule | At the Paraolympics if an athlete has an "A" Standard in an event they are allowed to enter events they have a "B" standard in. | 2016-07-25 | Phil | With the cost of travel and registration to Junior Nationals I propose tht an athlete be allowed to participate in events if they have a "B" standard time or distance. The "B" standard would be lets say 85% of the "A". This will also allow us to tighten the standards and not lose athletes. | Yes |  |  | Voted - Yes
5 | Field standards | Analyize Field standards to clean up standards which do not make sense to the members. | 2016-07-25 | Randy / Jess | 1. look at all 2016 results againnst all groups 2. Make recommendaations for changes prior to meeting . | Yes |  | Working | ok
6 | Track standards | Analyize standards verses | 2016-07-25 | Paul / Jess/Phil | 1. look at all 2016 results againnst all groups 2. Make recommendaations for changes prior to meeting . | Yes |  | Working | ok
7 | U11, U14 Field | Eliminate the 2016 U11 & U14 special Field rules of 5 minutes after athlete Is in the chair. | 2016-07-25 | Randy/Phil | After seeing that the new rules for field chair, athlete prep and warm up throws are not a problem, I would ask tht we vote to eliminate the special rules and go across the board with the IPC rules. | Yes | Adopt IPC rules for Seated Field with no exceptions except for U11 and U14 can have a minimum of up to 2 warm ups even if the time limit has expired |  | Voted - Yes
8 | National Limb Discrepancy Exemption | Create National Classifier form to be part of Classifiication and our Request for Limb exemption (field back of knee) that will be apart of the athletes class file. | 2016-07-25 | Denise/charlie | Denise to create a Classifiaction form that when a athlete presents with a legit limb Defficency the class team will sign a form givig the exemption. We will need to work how this information is known to the Officials in the pit. Could be a field in the class file in Sams and prinnts on the pit sheet. | Yes |  | Working | By 12/31/2016
9 | New Officials Test | Work with US Para and National ITO's to Create new Test For Officials | 2016-07-25 | Phil/Cathy/ Jerry | Work to complete by 11/1 and deliver at National Conference and at USATF annual meeting. | Yes | Develop New Course and Test. | Course in Review. Goal to have it Complete on Nov 1 | completed
10 | Publish Meet results and Psyc sheet | Work to publish weekly Sheets of National rankings from Meets and PoP forms | 2016-07-25 | Phil/Randy/Paul | We failed due to ASUSA not hving system in place. Work to acomplish this in 2017. | Yes |  | Working | Underway
11 | USATF/WTFSA partnership | Work to make Junior Nationals the Para JO's for USATF in2017 | 2016-07-25 | Phil/Debbie | Underway | Yes |  | Working | Agreed to by uSATF 12/1 in Orlando. Received 20K to proceed
12 | Road race Sanctioning | Expand Road race Sanctioning as a funding source. | 725/2016 | All | I need more than me bring in Road Race Money. Each of you need to get one race on board. Costs from 1500 all in to $150 sanction fee plus 10 per athlete. | Yes |  | Please explore adding races in your areas to get revenue to run Programs | Trying
13 | Redo of SAMS | Apart of item 10 | 2016-10-14 | Charlie/Phil/ Jimmy Cuevas/ Ralph/ Kevin Crytzer/Jessie | In order to get results we need the process and format to feed the database. We are working with NJIT in New Jersey to redo SAMS n SQL and Microsoft. We are planning a kick off meeting week of 10/24. Goal easier way to do Adaptive Track and Field Meet, | Yes |  | woithout ths we can't get results in a format that will post easily. Also a way to run Athletics meet for heating and seeding easily. | Underway
14 | 2017 Clinic | Track 2017 (field in 2016) | 2016-10-14 | Paul/Phil |  |  |  |  | Track 2017 at JN
15 | CP Records Process | How to treat Classes 35, 36, 37, 38 if the athlete's class changes and the athlete has a record in an age group | 2016-11-07 | Phil/Denise/Pam N | The ATFUSA process is to allow an athlete to keep records if their classification goes down and retire the record if the class goes up . This is fine for all classes except 35, 36, 37,38. For these CP classes the lower class does not guarentee that the assumption is true. It must be discussed and at worst ATFUSA must instigate a new process for these classes which would retire all records if an athlete with one of these classes goes up or down for both Track or Field. | Needs discussion |  | Discuss and form a position for a vote | exclude 35-38 from rule

## 2018
2019 Action Items for ATFUSA
V3_ 10/27/2018
No # | Item | Discription | Date in | Assign to | Discussion | Chair Position | Final Wording | COMMENTS/STATUS | Agreed or Not | Close Date
1 | Rule changes for the U14, U11, & Masters.
1a |  | Age Group change to align with WPA | 2018-09-20 | Phil, Paul, Randy | Change Age groups from U16, U18, U20 To U17, U20. | Change and Grand Father all Age Group Field set before 2018 in field, (Except for U16 records whch may not be using proper implement weights). Grand Father all U16, U18 records. | Due to WPA changing the Junior Age groups they control from U16, U18, U20 in 2018 to U17 nd U20 ATFUSA will n 2019 align with these age groups. The reason is necessary for Lienced athletes so they are running with their age group and in Field they are throwing the proper implement weights. | NOTE: ATFUSA made it known when WPA created the Junior age groups that U16, U18 and U20 were not the correct age groups and they should adopt the USA U17 and U20. Well 4 years later WPA discovered our view was the correct, due to numbers in each group not being a large enough population for good competition. | Agreed to at the 2017 national meeting with an implementation date of 2019.
2 | Clinics | Should be Track?? Athlete and Coaches |  |  | Athlete at Junior Nationals. -Due to comments from Junior Nationals it was thought smaller 3 hour sessions at a numer of Regional events would be better to give more personal training and give time between the Regional and JN to practice the skills learned at the Regional Session(s). CAF has positively responded to ths approcach and ay fund the sessions. Coaches at Annual Meeting. | Should be Track in 2019. Whch meetshould get the sessions (depending on available coaches).
3 | WEB Site Changes and Additions | Review Site and Make Recommendations For Adds/Deletes/Changes | 2018-08-01 | All | All board should review and comment
4 | Seated Field cage recommendations. | Update guidelines for L1, L2 and L3 meets with what we learned in 2018. | 2018-08-01 | R.C. /P.J. | The rulebook diagram shows the cage extending out 7 meters from the center line of the circle on each side. This is 22.9 feet with about 18 feet in front of the circle. Need to show all options with pictures on Website.
5 | PARA YOUTH CHAMIONSHIPS | try to get USATF to support | 2018-08-01 | Phil/ Pam/ Tom | 1. Need to better explain program 4. Set standards for 2019 and how to qualify. 5. Need to post results which add points in the Class/Agegroup results so agegroup winners can be determined immediately. 6. Discuss Medal process improvements | 1. Suggest for the ASUSA Junior National Athlete opt out rather than Opt in to compete. 2. Have a Medals Tent where athletes go and pick up there medals verses award ceremonies which were vere hard to fit in. 3. Work with USATF to better Advertise the championship so more than 16 from 1 team come.
6 | Neilsen Chairs to award | 1 track/1 field | 2017 | All to recommend | Still need to award chairs from Barry
7 | Master Championships | Find a sponsor to host Master championships | 2017 |  |  | Need to make money. Adult nationals deal is 150 + 5 per head > Our sponsor doc has it at 1500 flat . So it needs to be at at least 150+5 per head.
8 | National Record Certificate | Send out National Record Certificates |  | P.J. | We had agreed in 2016 to do this for Full ASUSA Memebers. Can we get it done for 2017?? | Asign??? But we need to modify the Excel and write the Access Report. (I have aproposed solution I created for IWAS championships I will send it out for approval.
9 | Classification DB on line | Classification DB on line like World Para Athletics. Change the YOB from a 2-digit field to a 4-digit field. | 2017 | P.J. | This is to standardize the two lists and provide a more reliable data point when matching records. | WAS THIS DONE???
10 | REVIEW FIELD Standards | F33 and others need to be looked at | 2018-08-01 | Randy/Dr. Darla/ all | Look at results some classes are well below the 50 to75% through to Junior Nationals goals | Need to review and make recommendations. After agegroup change
11 | Road Race Championship | for 15K, 5K, 1/2 and Marathon | ON GOING | PG & All | WE NEED MONEY TO DO THE PROGRAMS WE WANT TO DO | Please help me here!!!!
12
13 | Recognition for Kevin Crytzer | How can we say Thanks | 2018 | All | Award?? Gift?
14 | By-Laws | Really need to be brought up to date |  | All | We are not in compliance with our actions verses By-Laws and these must be reworked.
15 | SAMS updating | Review where we are and excellerate the completion. | on Going | All | Need to do Android app/ Need to complete on line meet management.
16 | work with ASUSA to repair shots | Any shots are in need to be sanded and painted to pass inspetion.
17 | Sell implements | Need to advertize and promote implement sales to raise money for program | On Going | All | Ideas to promote sales
18 | Hytek or other T&F meet manager with Records and class | Add records to Hytek and/or explore other software when SAMS is not used. | 2018-10-15 | All | Work with Paul Johnson on Hytek and see if Meet Pro would work. | Look at Meet pro because of cost and ability for licence use by all chapters.